## Supplier_Master
Supplier ID | Supplier Name | Country/Region | Service Category | Pre-Qual Status | Safety Index (1-5) | Payment Terms
1001 | ConcreteMix UAE | UAE | Direct Material | Approved | 4 | Net 30
1002 | Gulf Rebar Steel Co. | KSA | Direct Material | Approved | 5 | Net 45
1003 | EuroLift Rentals | Germany | Equipment Rental | Approved | 3 | Net 60
1004 | London MEP Services | UK | Subcontractor | Approved | 4 | Net 30
1005 | Al-Nujum Aggregates | UAE | Direct Material | Pending | 2 | Net 30
1006 | Italian Marble & Stone | Italy | Direct Material | Approved | 5 | Net 60
1007 | Saudi Scaffolding | KSA | Equipment Rental | Approved | 4 | Net 45
1008 | German Electrical | Germany | Subcontractor | Pending | 3 | Net 30

## Material_Master
Material ID | Material Description | Material Group | Project Cost Code | Unit of Measure | Standard Price (USD)
M101 | Steel Rebar (Grade 60) | Structural Steel | P-STR-001 | MT | 750
M102 | Ready-Mix Concrete C40 | Wet Concrete | P-CON-002 | M3 | 95
M103 | Scaffolding Rental | Equipment Rental | P-EQP-003 | Day | 120
M104 | HVAC Subcontract Service | Subcontractor | P-MEP-004 | Lot | 85000
M105 | Granite Countertops | Finishes | P-FIN-005 | SQM | 150
M106 | Standard Cement Bags | Dry Material | P-CON-002 | Bag | 5
M107 | Electrical Installation | Subcontractor | P-MEP-004 | Lot | 55000

## Contracts_RFQ
Contract ID | Supplier ID | Material ID | Type (MAS/RFQ) | Negotiated Price/Rate | Contract End Date | Max Order Value | Status
C-001 | 1002 | M101 | MAS | 745 | 2026-12-31 | 500000 | Active
C-002 | 1001 | M102 | MAS | 94 | 2025-06-30 | 250000 | Active
C-003 | 1003 | M103 | MAS | 115 | 2024-11-30 | 50000 | Expiring
R-101 | 1004 | M104 | RFQ | 84500 | 2025-09-01 | 84500 | Awarded
R-102 | 1008 | M107 | RFQ | 57000 | 2026-03-30 | 57000 | Awarded
C-004 | 1005 | M106 | MAS | 5.5 | 2026-06-30 | 100000 | Active

## Purchase_Orders_GR
PO Number | Project ID | PO Date | Required Delivery Date | Actual Delivery Date | Supplier Name | Supplier ID | Material ID | Quantity | Unit Price (PO) | Total Value | Quality Accepted (Y/N)
P-1001 | Burj-2025 | 2025-01-05 | 2025-01-15 | 2025-01-15 | Gulf Rebar Steel Co. | 1002 | M101 | 200 | 745 | 149000 | Y
P-1002 | Euro-HQ | 2025-01-10 | 2025-01-20 | 2025-01-22 | ConcreteMix UAE | 1001 | M102 | 500 | 94 | 47000 | Y
P-1003 | Burj-2025 | 2025-01-12 | 2025-01-18 | 2025-01-25 | EuroLift Rentals | 1003 | M103 | 100 | 120 | 12000 | N
P-1004 | Euro-HQ | 2025-01-15 | 2025-02-01 | 2025-02-01 | London MEP Services | 1004 | M104 | 1 | 84500 | 84500 | Y
P-1005 | KSA-Res | 2025-01-20 | 2025-01-30 | 2025-01-30 | Al-Nujum Aggregates | 1005 | M106 | 5000 | 5.8 | 29000 | Y
P-1006 | Burj-2025 | 2025-02-01 | 2025-02-10 | 2025-02-15 | Gulf Rebar Steel Co. | 1002 | M101 | 150 | 750 | 112500 | Y
P-1007 | KSA-Res | 2025-02-05 | 2025-02-15 | 2025-02-14 | ConcreteMix UAE | 1001 | M102 | 300 | 94 | 28200 | Y
P-1008 | Euro-HQ | 2025-02-10 | 2025-02-20 | 2025-02-20 | German Electrical | 1008 | M107 | 1 | 57000 | 57000 | Y
P-1009 | Burj-2025 | 2025-02-15 | 2025-02-25 | 2025-02-28 | Al-Nujum Aggregates | 1005 | M106 | 4000 | 5.5 | 22000 | N
P-1010 | KSA-Res | 2025-03-01 | 2025-03-10 | 2025-03-10 | Italian Marble & Stone | 1006 | M105 | 200 | 150 | 30000 | Y
P-1011 | Euro-HQ | 2025-03-05 | 2025-03-15 | 2025-03-17 | EuroLift Rentals | 1003 | M103 | 150 | 115 | 17250 | Y
P-1012 | Burj-2025 | 2025-03-10 | 2025-03-20 | 2025-03-20 | Gulf Rebar Steel Co. | 1002 | M101 | 100 | 745 | 74500 | Y
P-1013 | Euro-HQ | 2025-03-15 | 2025-03-25 | 2025-03-25 | ConcreteMix UAE | 1001 | M102 | 600 | 95 | 57000 | Y
P-1014 | KSA-Res | 2025-03-20 | 2025-03-30 | 2025-04-03 | Al-Nujum Aggregates | 1005 | M106 | 3000 | 5.6 | 16800 | N
P-1015 | Burj-2025 | 2025-04-01 | 2025-04-10 | 2025-04-10 | London MEP Services | 1004 | M104 | 1 | 85000 | 85000 | Y
P-1016 | KSA-Res | 2025-04-05 | 2025-04-15 | 2025-04-15 | Saudi Scaffolding | 1007 | M103 | 50 | 125 | 6250 | Y
P-1017 | Euro-HQ | 2025-04-10 | 2025-04-20 | 2025-04-21 | German Electrical | 1008 | M107 | 1 | 57500 | 57500 | Y
P-1018 | Burj-2025 | 2025-04-15 | 2025-04-25 | 2025-04-25 | Gulf Rebar Steel Co. | 1002 | M101 | 100 | 745 | 74500 | Y
P-1019 | KSA-Res | 2025-04-20 | 2025-04-30 | 2025-05-02 | Al-Nujum Aggregates | 1005 | M106 | 6000 | 5.5 | 33000 | Y
P-1020 | Euro-HQ | 2025-04-25 | 2025-05-05 | 2025-05-05 | Italian Marble & Stone | 1006 | M105 | 100 | 155 | 15500 | Y